## WBS
# | Task | Description | Assigned To | Est. Hours | Dependencies | Status
Phase 1: Setup & Configuration
1 | Setup Development Environment | Install Python 3.10+, Node.js 18+, create project folder, initialize virtual environment, install dependencies from requirements.txt (microsoft-agents SDK, aiohttp, python-dotenv) | Dev 1 | 2 | -
2 | Create .env Configuration | Copy .env.template to .env, configure KONG_API_URL (pointing to existing Lambda /chat endpoint), KONG_FEEDBACK_URL, MicrosoftAppId, MicrosoftAppPassword, PORT | Dev 1 | 1 | 1
Phase 2: Bot Handler Development (bot_handler.py)
3 | Build call_km_agent() Function | Implement async HTTP POST function using aiohttp that sends user question and session_id as JSON to KONG_API_URL, handles 60-second timeout, parses JSON response on HTTP 200, returns user-friendly error dict on failure | Dev 1 | 3 | 1
4 | Build send_feedback() Function | Implement async HTTP POST function that sends correlation_id, feedback_type, and comment to KONG_FEEDBACK_URL with 10-second timeout. Graceful error handling. Pre-built for future Adaptive Card integration | Dev 1 | 1.5 | 1
5 | Build format_teams_response() Function | Implement response formatter that extracts answer, citations, sources, intent from Lambda JSON and assembles a readable Teams message with clickable Markdown source links [title](url) and category tag | Dev 1 | 2 | 3
6 | Build Welcome Message Handler | Implement @conversation_update('membersAdded') event handler that sends greeting message with bot description and example questions when a user first opens a chat with the bot | Dev 1 | 1 | 1
7 | Build Main Message Handler | Implement @activity('message') handler: extract user question from context.activity.text → validate input → show typing indicator → call call_km_agent() with conversation.id as session_id → format response → send back to user | Dev 1 | 2.5 | 3,5
8 | Build Server Startup Block | Implement __main__ entry point: log configuration on startup (port, Kong URL, messaging endpoint), start aiohttp server via start_server() on configured PORT, handle startup failures with error logging | Dev 1 | 1 | 6,7
Phase 3: Teams App Package (appPackage/)
9 | Create manifest.json | Write Teams app manifest with schema v1.19: define bot ID, scopes (personal, team, groupChat), permissions (identity, messageTeamMembers), validDomains. Leave {{APP_ID}}, {{AZURE_BOT_ID}}, {{BOT_HOSTING_DOMAIN}} as placeholders for client | Dev 1 | 1.5 | -
10 | Create App Icons | Design or source two app icons: color.png (192x192 px, full-color) and outline.png (32x32 px, transparent outline). Set accentColor hex value in manifest | Dev 1 | 1 | -
11 | Validate App Package | Verify manifest.json against Microsoft schema, confirm icons meet size requirements, test zip packaging (cd appPackage && zip -r ../km-bot.zip *), validate package can be uploaded to Teams Admin Center | Dev 1 | 1 | 9,10
Phase 4: Local Testing
12 | Test with Agents Playground | Install @microsoft/agents-playground via npm, run bot on localhost:3978, test in playground UI: verify welcome message appears → send questions → verify formatted responses with citations → test empty message handling | Dev 1 | 2 | 8
13 | Test Error Scenarios | Test: Lambda endpoint unreachable → verify friendly error message returned. Request timeout (>60s) → verify timeout error. Empty/whitespace message → verify prompt to type question. Malformed Lambda response → verify bot doesn't crash | Dev 1 | 1.5 | 12
Phase 5: Documentation & Packaging
14 | Write README.md | Document: project overview, architecture diagram (Teams → Azure Bot → Kong → Bot Handler → Lambda), package contents table, placeholder reference table, local testing steps with Agents Playground, deployment steps, API contract (request/response JSON) | Dev 1 | 2 | 12
15 | Write Handoff Guide (DOCX) | Create client-facing handoff document: what is delivered vs what client sets up, end-to-end architecture flow, step-by-step Azure Bot registration, hosting options, manifest placeholder replacement, Teams app deployment via Admin Center | Dev 1 | 3 | 12
16 | Create .env.template | Create environment variables template with placeholder values and descriptive comments for each variable: KONG_API_URL, KONG_FEEDBACK_URL, MicrosoftAppId, MicrosoftAppPassword, MicrosoftAppType, PORT | Dev 1 | 0.5 | -
17 | Code Review & Comment Cleanup | Review bot_handler.py: ensure professional descriptive comments on every section, proper error handling in all functions, no hardcoded secrets or real URLs, no debug/test code left behind, consistent code style | Dev 1 | 1.5 | 8
18 | Assemble Final Zip Package | Package all deliverables into KM_Agent_Teams_Bot_Package.zip: bot_handler.py, requirements.txt, .env.template (no real secrets), README.md, Teams_Bot_Handoff_Guide.docx, appPackage/ (manifest.json, color.png, outline.png). Verify completeness | Dev 1 | 1 | 14,15,16,17

## Summary
Phase | Tasks | Est. Hours
Phase 1: Setup & Configuration | 2 | 3
Phase 2: Bot Handler Development | 6 | 11
Phase 3: Teams App Package | 3 | 3.5
Phase 4: Local Testing | 2 | 3.5
Phase 5: Documentation & Packaging | 5 | 8
TOTAL | 18 | 29
Working Days (6 hrs/day) |  | ~5 days